## Sheet1
CMPUT301W18T16
RELEASE PLANNING BREAKDOWN
Project Part | User Type | Use Case | Related User Stories | Dependent Use Cases | Comments
Project Part 4
4 | requester | 1. Add a task | US 01.01.01
4 | requester | 2. Set max. length of task title (30 char.) | US 01.01.02 |  | 20170214 added
4 | requester | 3. Set max. length of task desc. (300 char.) | US 01.01.03 |  | 20170214 added
4 | requester | 4. View my task list | US 01.02.01 | 1
4 | requester | 5. Edit my tasks | US 01.03.01 | 7
4 | requester | 6. Delete my task | US 01.04.01 | 7
4 | requester/provider | 7. View task details | US 02.01.01
REPLACEME | requester/provider | 8. Assign task status | US 02.02.01 | 7
4 | provider | 12. Adv. Search in all tasks | US 04.01.01
4 | provider | 21. View tasks I am assigned | US 06.01.01
4 | requester | 22. View my assigned tasks | US 06.02.01
4 | requester | 26. Attach 1+ picture to my task | US 09.01.01 | 7
4 | requester/provider | 27. View picture for a task | US 09.02.01 | 7
4 | system admin | 28. Set Picture size < 65536 Bytes | US 09.03.01 | 26
4 | user | Log in page
4 | user | Sign up page
Project Part 5
5 | user | 9. Set user profile | US 03.01.01
5 | user | 10. Edit user profile | US 03.02.01 | 9
5 | user | 11. View other user's profile | US 03.03.01 | 7
5 | provider | 13. View search results | US 04.02.01 | 12
5 | provider | 14. Bid on task | US 05.01.01 | 13
5 | provider | 15. View tasks I bidded on | US 05.02.01 |  | 20170214 revised
5 | requester | 16. my bidded task notification | US 05.03.01 |  | could use a snackbar
5 | requester | 17. View my bidded tasks | US 05.04.01
5 | requester | 18. View bid | US 05.05.01 | 17
5 | requester | 19. Accept bid on my task | US 05.06.01 | 17
5 | requester | 20. Decline bid on my task | US 05.07.01 | 17
5 | requester | 23. Assigned -> Done | US 07.01.01 | 22
5 | requester | 24. Assigned -> Requested | US 07.02.01 | 22
5 | requester | 25. Add/Edit tasks offline | US 08.01.01 | 5 6 7
5 | requester | 29. Add geo location for a task, on a map | US 10.01.01 | 7
5 | requester | 30. View geo location for a task, on a map | US 10.02.01 | 7 30
5 | provider | 31. See tasks with status within 5 KM on a map | US 10.03.01
5 | REPLACEME | 32. Rate a user |  | 11